Workflow Plan for Mentoring Small Business Owners using the FAMILY Framework

Objective

- To mentor up to 10 small business owners through the FAMILY framework.

- To meet virtually via Zoom for 1 hour every week for a total of 24 weeks.

- To assist these owners in generating more business and creating a solid 6-month strategy that they can execute daily.

Pre-Mentorship (Week 0)

Tasks

- Initial Outreach

  - Email small business owners to invite them to participate in the mentorship program.

- Screening and Onboarding

  - A short questionnaire to assess their current business challenges, goals, and familiarity with virtual meeting tools.

- Introductory Meeting (Zoom)

  - Introduce the FAMILY framework.

  - Set expectations for the mentorship program.

- Preparation

  - Create individual folders for each participant to store resources, notes, and plans.

Tools

- Email

- Google Forms for Questionnaire

- Zoom

- Google Drive

Weekly Mentorship Plan (Weeks 1-24)

Weekly Agenda

Week 1: F - Financial Planning

- Understanding financial health

- Importance of budgeting

- Introduction to cash flow management

Week 2: A - Analytics & Assessment

- How to measure success

- Key Performance Indicators (KPIs)

Week 3: M - Marketing Strategies

- Basic marketing channels

- Identifying target customers

Week 4: I - Innovation

- Innovating within your industry

- Introduction to SWOT analysis

Week 5: L - Leadership and Team Building

- Hiring and team building

- Leadership skills in crisis

Week 6: Y - Yield Management

- Maximizing profits

- Inventory and time management

Weeks 7-12: Deep Dive into Each Framework Component

- Detailed breakdown and planning for each FAMILY component.

Weeks 13-18: Strategy Building

- Compile insights from previous weeks into a cohesive strategy.

Weeks 19-23: Execution & Feedback

- Work on executing the plan.

- Weekly feedback and adjustments.

Week 24: Final Review & Future Planning

- Assess the six-month journey.

- Develop an action plan for the next six months.

Weekly Tools

- Zoom (for meetings)

- Shared Google Drive (for resources)

- Excel or Google Sheets (for tracking KPIs)

- Slack or Email (for communication between meetings)

Post-Mentorship (Week 25 onwards)

- Follow-Up Survey

  - To gather feedback and assess the effectiveness of the mentorship program.

- Certificate of Completion

  - Digital certificates emailed to participants.

- Continued Support

  - Quarterly check-ins for the next six months via Zoom or email.

- Community Building

  - Inviting participants to join a LinkedIn group or Slack channel for ongoing support and networking.

Tools

- Google Forms (for feedback)

- Zoom or Email (for continued communication)

- LinkedIn or Slack (for community building)

By following this workflow plan, the aim is to guide small business owners through a structured journey that will help them generate more business and create a robust 6-month strategy.

The cost of providing mentorship services like the one outlined in the FAMILY framework varies depending on a number of factors:

- Expertise of the Mentor: If the mentor is highly skilled and has a proven track record, they can charge more for their services.

- Material Costs: This includes any software subscriptions, research materials, or other tools used in the mentorship program.

- Time Commitment: A one-hour per week commitment is less demanding than a program that requires multiple hours per week, and the pricing should reflect that.

- Group Discount: As this program is aimed at mentoring up to 10 small business owners at the same time, a group rate could be offered, which is generally lower than one-on-one coaching rates.

- Additional Services: If the program includes other services like email support, resource materials, or assessments, this can also affect the cost.

Pricing Models

- Flat Fee: A one-time charge for the entire 6-month program.

- Weekly Payments: A recurring payment that occurs every week for the duration of the program.

- Monthly Payments: A monthly fee for the course of the mentorship.

Sample Pricing

- Flat Fee: $2,400 - $4,800 per business owner for the entire 6 months.

- Weekly Payments: $100 - $200 per week, which would equate to approximately $2,400 - $4,800 over the course of 24 weeks.

- Monthly Payments: $400 - $800 per month, which also equals $2,400 - $4,800 for the entire 6-month program.